## Slide 1: Agenda Item 11 Status of Projects under Strategic Development Plan of IFPP 2017-19
SAI-India
11th Meeting of KSC Steering Committee
Pampanga, Philippines
(12-14 June 2019)

## Slide 2: Projects under current SDP
SDP emphasized the need to work on Consolidation and aligning of existing literature/ guidance on specific subjects of Audit with ISSAI 100.
4 projects under the SDP are of this nature.
3 projects are in the nature of new products.
These will lead to 9 pronouncements in the IFPP.

## Slide 3
Project 2.7
Audit of Privatisation
(India)
Project 2.7
Audit of PPP
(Ecuador)
Project 2.8
IT Audit
(India)
Project 2.9
Audit of Public Debt
(Philippines)
Project Proposal
Exposure Draft
Endorsement Version
Team Working on Exposure Draft
Proposal forwarded to FIPP
Endorsement version forwarded to FIPP
Exposed for Public
Approved by FIPP

## Slide 4
Project 2.10
Audit of Disaster Related Aid
(ECA)
Project 2.11
Audit of Public Procurement
(Russia)
Project 2.12 Jurisdictional Activities of SAIs
(France)
Project 3.10
Audit of KNI
(Russia)
Team Working on Exposure Draft
Endorsement version forwarded to FIPP
Revised Exposure Draft forwarded to FIPP
Endorsement version forwarded to FIPP
Project Proposal
Exposure Draft
Endorsement Version
Approved by FIPP

## Slide 5: Status of projects under current SDP
SDP Ref | Project Name/ lead SAI | Status
2.7 | Audit of Privatisation & PPP -India , Ecuador | GUID on audit of Privatisation (SAI India) Project proposal approved by FIPP. Team working on the exposure draft. GUID on Audit of Public-Private Partnerships (SAI Ecuador) Project proposal forwarded to FIPP. Projects to be completed by 2020 INTOSAI GB.
2.8 | IT Audit -India | GUID on audit of Information system (GUID 5100) GUID on Audit of Information System Security (GUID 5101) Exposure period ended on 24th April, 2019. Endorsement versions forwarded to FIPP in June Project expected to be completed by XXIII INCOSAI.

## Slide 6: Status of projects under current SDP
SDP Ref | Project Name/ lead SAI | Status
2.9 | Audit of Public debt (GUID) -Philippines | Exposure draft approved by FIPP. Presently exposed for public consultation till 23rd August. Project expected to be completed by 2020 INTOSAI GB.
2.10 | Audit of Disaster related aid (GUID) -ECA | Project proposal approved. Team working on Exposure draft. Project envisaged to be completed by 2020 INTOSAI GB.
2.11 | Audit of Public Procurement (new GUID) -Russia | Revised Exposure draft forwarded to FIPP Project to be completed by 2020 INTOSAI GB.

## Slide 7: Status of projects under current SDP
SDP Ref | Project Name/ lead SAI | Status
2.12 | International Pronouncement on Jurisdictional Activities of SAIs (new INTOSAI P) -France | Endorsement version forwarded to FIPP. Project expected to be completed by XXIII INCOSAI.
3.10 | Audit of KNI (new GUID) -Russia | Endorsement version forwarded to FIPP. Project expected to be completed by XXIII INCOSAI.

## Slide 8: SDP 2020-22 (proposed)

## Slide 9: SDP 2020-22 (proposed)
      Being coordinated by PSC.
      Based on inputs received from the INTOSAI wide consultation exercise and FIPP’s own scanning exercise.
      Focus on
        Reviewing the present IFPP framework
        Refining the concepts
        Define a uniform structure and format of the pronouncements.
        Scoping the projects to be taken up in the following SDP.

## Slide 10: SDP 2020-22 (proposed)
Initiatives are crosscutting in nature and therefore cannot be assigned to a single INTOSAI body.
Goal Chairs will be jointly responsible for the overall coordination for the implementation of the plan.
    SDP 2020-22 was deliberated at the PSC Steering committee (4-6 June 2019)
    PSC-SC wants feedback from KSC and CBC Steering Committees
    Circulated to all members of KSC Steering Committee
WGs may provide their comments on the SDP by June end.

## Slide 11: THANK YOU

## Slide 12: SDP 2020-22 – List of Initiatives
    Define structure and format for INTOSAI P, ISSAIs, COMPs (Competency standards).
    Comparing and refining concepts used across the framework.
    Gather evidence to assess the relevance and suitability of the current framework and use the insight to update and refine the framework.
    To prepare a revised conceptual framework for an improved IFPP to enable clear, relevant and consistent standards.
    Relevance of Lima Declaration- How to treat it as historic document
    Scoping of Project revision of ISSAI 140
    Scoping - Complete Migration of GUIDs to new Framework, revise/withdrawal of pre-IFPP documents
    Scope – assessment on how IFPP can provide assistance in relation to audit of SDGs and Fraud, corruption and other irregularities.
    Competency Pronouncements.