Strategic objectives review report (15.05.2019)

For Strategic Objective 3 of the INTOSAI Strategic Plan 2017-22

| Strategic objective (as per SP 2017-22) | Strategies & initiatives (as per SP 2017-22) | Performance indicator | Action items and other comment |
| --- | --- | --- | --- |
| Develop and maintain expertise in the various fields of public-sector auditing and help to provide content to the INTOSAI Framework for Professional Pronouncements | Preparation of new INTOSAI products and product lines: The KSC, in collaboration with other INTOSAI entities, has work plans and milestones for development of new standards and guidance for consideration by the common forum, and other INTOSAI products during 2017–2022. The KSC works closely with other stakeholders to develop products for INTOSAI’s efforts to support the implementation where appropriate and contribute to the follow-up and review of the SDGs. | 1. Initial assessment and Project proposal to the INTOSAI GUID for Public Procurement audit were developed and approved by FIPP. 2. Exposure draft to the INTOSAI GUID for Public Procurement Audit was developed. 3. Draft Exposure draft of the GUID was approved by the WGPPA members and submitted to INTOSAI bodies for the review according to the Due Process. | Progress to date: 1. In December 2016, the INTOSAI Working Group on Public Procurement Audit (hereinafter referred to as the "Working Group") was established, which included 17 SAIs 2. In July 2017, the first meeting of the Working Group was held in Lisbon (Portugal) with the following results: - the Terms of Reference and the Working Plan of the Working Group for 2017-2019 were approved. - the relevance and necessity of the GUID was recognized. 3. Project proposal to the GUID was formed. In 2017 proposals from the members of WG on the content of the GUID were submitted. |
|  |  | Draft Exposure draft of the GUID was submitted to FIPP in August, November and March but hasn’t passed the approval process. The schedule is being revised. The GUID is planned to be endorsed at GB 2020 | The Project proposal on the GUID for Public Procurement audit was submitted to the FIPP at the end of 2017 The Exposure draft on the GUID was developed and sent for consideration to the WGPPA members. The document was approved by the members of WGPPA at the 2nd meeting of the group in July 2018. The Exposure draft on the GUID was sent for the review to KSC, FIPP and FAAS, PAS and CAS. The Exposure draft was submitted to FIPP meetings in August, November and March but hasn’t passed the approval process. Necessary amendments need to be done. The revised version is being developed. Action items/key next steps: Revising of the Exposure draft and further approval by FIPP. Further steps of the development of the GUID in compliance with the Due Process. Endorsement of the GUID at the Governing Board 2020 |
|  | Revision of ISSAI products: Annual targets for updating and revising existing standards are established for the period 2017–2022. This work is done in close collaboration with the PSC and FIPP. | – | – |
| Enable wide exchange of knowledge and experience among INTOSAI members. | INTOSAI KSC-IDI Community Portal: In close collaboration with IDI, a knowledge sharing platform to serve as the hub for knowledge sharing has been formed.. | Further development of the methodical base, the information exchange system and information resources in the field of Public Procurement Audit | In 2017 the WG website was formed (the information is presented at the official website of the Accounts Chamber of the Russian Federation at the following link: http://www.ach.gov.ru/en/wgppa_en.php?clear_cache=Y |
|  | Research projects: The KSC leads the development of a scheme for encouraging internal (to INTOSAI) and external research projects in public audit. The KSC also facilitates INTOSAI’s engagement with the academic community on issues of mutual interest and concern. | The Accounts Chamber of the Russian Federation engagement with the scientific organization for the work of the Working Group | The State Research Institute of System Analysis of the Accounts Chamber of the Russian Federation was engaged for the work on the Standard in 2017 . |
|  | Generation and dissemination knowledge and experiences. (workshops, training, benchmarking exercise, joint/ collaborative audits, outreach activities etc.) | Exchange of experience on the practice of auditing in the field of Public Procurement between the members of the Working Group | During the first meeting of the Working Group held in Lisbon (Portugal) in July 2017, the experience and practice of public procurement auditing of the SAIs of Kuwait, Pakistan, Serbia, Thailand, Armenia and Portugal were presented and discussed. During the 2nd meeting of the WG held in Serbia in June 2018 the experience and practice of public procurement audit of SAI Serbia, SAI Philippines, SAI Slovenia, SAI Kuwait were presented and discussed. |
| Working with the CBC, IDI, and other INTOSAI entities, facilitate continuous improvement of SAIs through knowledge sharing on the crosscutting lessons learned from the results of peer reviews and SAI PMF. | Stakeholder engagement: The KSC, other strategic goal committees, IDI, INTOSAI regional organizations, the Supervisory Committee on Emerging Issues and the INTOSAI General Secretariat work together to avoid duplication of work and for greater synergy. | Cooperation with the INTOSAI bodies in the development and promotion of the draft GUID | While developing the GUID, the consultations with FAAS, CAS and PSC were made. The information can also be exchanged with the INTOSAI Working Group on the Fight Against Corruption and Money Laundering. Moreover, some of the members that were drafting the GUID are representatives of the Forum for Jurisdictional SAIs. |
|  | Facilitate continuous improvement: Working with the CBC, IDI, and other INTOSAI entities, the KSC gathers and disseminates crosscutting lessons learned from the individual results of peer reviews and of SAI PMF assessment. | Exchange of experience on the practice of auditing in the field of Public Procurement | The Working group is ready to exchange experience of auditing in the field of Public Procurement and methodological developments in this area. . |
|  | Cooperate with and leverage the efforts of The International Journal of Government Auditing and the General Secretariat to expand the use of social media, video, and interactive tools to ensure “real-time” communication across INTOSAI, its partners, and with other interested parties | Participation in the preparation of information materials on the Working Group activities | The Accounts Chamber of the Russian Federation is ready to prepare for the Journal information on the Working Group, its actual goals and objectives of its activities. |

# Footnotes

In the case of single large projects / initiatives, the progress indicator could also be one of the following three progress statements: (i) the project has been initiated/come into existence (has been defined, planned , and resourced),  (ii) the project is being implemented (and is on track, or behind schedule, in trouble – green or amber or red/Purple), and (iii) the project has delivered the main outcome (is either completed – black – or its outcome is functioning as intended / producing the results, e.g. a technical support function;  maintain, monitor and enhance). Appropriate colour may be chosen as the background of the cell.

SP 2017-22, page 36, refers to the strategic objectives review to include “determining what actions and next steps are most needed to ensure continued progress towards each objective”.  The progress achieved till date and the key items/next steps needed to ensure continued progress towards each objective and to manage risks may be indicated here.

A row may be added for each activity like Workshop, trainings, benchmarking exercise, joint/ collaborative audits, outreach activities etc.

# Text boxes

KSC work plan 2017-19

Key to progress indicator colours

|  | Initiatives / projects on schedule |
| --- | --- |
|  | Initiatives / projects behind schedule |
|  | Serious difficulties being experienced – Internal factors |
|  | Serious difficulties being experienced – External factors (beyond the control of the WG) |
|  | Not yet scheduled to start |
|  | Initiatives / projects completed |

Report of the INTOSAI Working Group on Public Procurement Audit