## Slide 1: Strategic Development Plan of IFPP 2017-19 and 2020-25
SAI-India
10th Meeting of KSC Steering Committee
Kampala
(20-24 August 2018)

## Slide 2: Progress of projects under current SDP-IFPP
Project | Name of the Project | Status
2.7 (Project team to be formed) | Consolidating and aligning guidance for audits of Privatization & PPP with ISSAI 100 | GUID on audit of Privatization GUID on Audit of Public-Private Partnerships Project proposals forwarded to FIPP for consideration. Project team to be constituted after approval of the project proposal by FIPP
2.8 (India) | Consolidating and aligning guidance on IT Audit with ISSAI 100 | GUID on audit of Information system (GUID 5100) GUID on Audit of Information System Security (GUID 5101) Exposure draft forwarded to FIPP for consideration

## Slide 3: Progress of projects under current SDP-IFPP
Project | Name of the Project | Status
2.9 (Philippines) | Consolidating and aligning guidance on audit of Public debt with ISSAI 100 | 1. The due date for submission of the exposure draft extended from 10th July to 9th October
2.10 (Project team to be formed) | Consolidating and aligning guidance on audit of Disaster related aid with ISSAI 100 | GUID on audit of Disaster related aid Project proposal forwarded to FIPP. Project team to be constituted after approval by FIPP
2.11 (Russia) | Consolidating and aligning guidance on audit of Public Procurement with ISSAI 100 | Exposure draft forwarded to FIPP.

## Slide 4: Progress of projects under current SDP
Project | Name of the Project | Status
2.12 (France) | International Pronouncement on Jurisdictional Activities of SAIs | 1. Project Proposal revised to develop Fundamental Principles of Jurisdictional activities of SAIs 2. Revised Project proposal will be forwarded to FIPP after deliberations at this KSC SC meeting
3.10 (Russia) | Consolidating and aligning guidance on audit of KNI with ISSAI 100 | Exposure draft forwarded to FIPP.

## Slide 5: Recommendation of FIPP: 2.7 Consolidation and aligning Guidance on audit of Privatization with ISSAI 100
  Prelim team constituted to assess the need of pronouncements in this area
  Team members: USA, China, ECA, Philippines, Fiji and India
  Report discussed in 7th FIPP meeting in March 2018; FIPP recommended:
    Develop GUID on Audit of Privatization (drawing on the pre-existing ISSAI 5210)
    Develop a GUID on Public-Private Partnerships (drawing on the pre-existing ISSAI 5240)
  Considering their relevance and the challenge in developing a separate GUID.
    Withdrawal of ISSAIs 5220 on Guidelines on Best Practice for the Audit of Public/Private Finance and Concessions
    Withdrawal of ISSAI 5230 on Guidelines on Best Practice for the Audit of Economic Regulation

## Slide 6: Recommendation of FIPP: 2.10 Consolidation and aligning Guidance on audit of disaster related aid with ISSAI 100
  Presently five ISSAIs and one INTOSAI GOV on Disaster related aid
  Preliminary team constituted to assess the requirement of ISSAIs
  Recommended a single GUID on disaster-management (drawing on and consolidating the pre-existing ISSAIs 5500, 5510 and 5520)
    covering audits of preparedness (management before the disaster) as well as audits of aid (management after the disaster)
  To include as an annex risk of Fraud and corruption in emergency phase after disaster (drawing from ISSAI 5530)
  Withdrawal of:
  ISSAI 5540 - Use of Geospatial Information in Auditing Disaster Management and Disaster-related Aid
  INTOSAI GOV 9250 - Integrated Financial Accountability Framework (IFAF)

## Slide 7: Points for consideration
  To mitigate risk of delay in the approvals, WGs requested to share intermediate drafts with FIPP LOs for review
  FIPP requires at least one opportunity to consider a draft at physical FIPP meeting before approval
  According to interpretation approved by 70th INTOSAI Governing Board, new and revised pronouncements can take effect after the Governing Board has referred them for final endorsement to INCOSAI
  Project groups can work with perspective of having new pronouncements entering the Framework yearly, after Governing Board’s approval
    need not wait for INCOSAI

## Slide 8: Calendar for next SDP 2020-25

## Slide 9: SDP 2020-25
WG to forward proposal to PSC by 5th October.
Only proposal that fits the prescribed criteria to be considered.
Project under Priority 3 will not automatically qualify for next SDP
FIPP suggestion, the initial assessment may be followed by project proposal in the prescribed template to save time in approvals

## Slide 10: Discussion issues
Working groups inputs on criteria specified by PSC SC on selection of Projects for next SDP
Has Working Group identified any projects for next SDP of IFPP?

## Slide 11: THANK YOU