Key to progress indicator colours

|  | Initiatives / projects on schedule |
| --- | --- |
|  | Initiatives / projects behind schedule |
|  | Serious difficulties being experienced – Internal factors |
|  | Serious difficulties being experienced – External factors (beyond the control of the WG) |
|  | Not yet scheduled to start |
|  | Initiatives / projects completed |

Reporting dashboard - Working Group on Big Data (SAI China)

KSC work plan 2017-19

Strategic objectives review report (as on August 18, 2017)

| Strategic objective (as per SP 2017-22) | Strategies & initiatives (as WGBD TOR) | Performance indicator | Action items and other comment |
| --- | --- | --- | --- |
|  | Identify the opportunities and challenges that SAIs are facing in a big data world to provide recommendations to SAIs. Summarize the know-how, experiences and good practices concerning big data audit, to help SAIs boost relevant skills. Develop guidelines and research reports, to share knowledge and support capacity building activities in big data audit. Strengthen bilateral, regional and INTOSAI-wide cooperation among SAIs in big data audit. | I. Meetings and seminars 1.Symposiums and seminars A seminar on challenges and opportunities faced by supreme audit institutions (SAIs) in a big data world is to be held in April 2017. 2.Working group meetings WGBD will host its meetings annually. The first WGBD meeting will be held in April 2017 in China, which will determine the WGBD terms of reference, work plan and research projects. II. Research projects and publications From the year 2017, WGBD will organize research projects on changes within SAIs in the era of big data. The topics shall be determined by WGBD members. The research projects should focus on the applications of big data as well as changes and best practices in various SAIs’ audit approaches, organizational modes and audit results. WGBD will publish research papers with guiding significance at certain stage of the research. III. Cooperation and communication | Progress to date Working Group on Big Data (WGBD) successfully established, and 1 meetings held. In the meeting delegates discussed the challenges and opportunities: 1) national policies should support the work of government auditors; 2) a variety of big data technologies should be applied to carry out audit activities; 3) IT infrastructure construction is critical to the big data audit. Delegates all agreed that it is necessary and urgent to apply data analytic in auditing, and expected more sharing of information, knowledge and technology related to big data on the platform of the Working Group. Based on Survey on Research Topics, we are going to focus on Auditing Technologies Innovation and Big Data Audit Practice. A website of the Working Group is set up for communication Action items / key next steps: The Working Group would organize research teams and launch the project in Fall 2017 |