## Slide 1
PROGRESS REPORT Research Project on Auditing Emergency Preparedness of Disaster
10th KSC meeting
Kampala, 21st August 2018
Notes: Good afternoon ladies and gentlemen.
Thank you for the time given to the Audit Board of the Republic of Indonesia to present progress report of research project on Auditing Disaster Preparedness.

## Slide 2: AGENDA
1
2
3
GENERAL OVERVIEW
PROJECT DESIGN
PROGRESS TO DATE
Notes: We will deliver this session into three agenda: general overview of the project, project design, and proposed deliverable.
General overview will bring us to get acknowledged with project background, project objectives, responsible SAIs, activities and coordination arrangement, and progress to date. Meanwhile, project design will look at project scope, planned methodology, and timeframe of this project. Then, we will present you with proposed outline of the research project.
We also invite you to discuss issues regarding our proposed outline of the research project.

## Slide 3: 1. GENERAL OVERVIEW

## Slide 4
2trilion $ Economic loses
4.4 billion affected And claimed 1.3 million lives
Effects will be worsen In 2030
SDGs Point 1,2,3 & 16
Project BACKGROUND
Notes: Disasters have a devastating impact on development. Families lose homes, livelihoods and loved ones; communities and nations lose businesses, jobs and services; and children miss school, impacting on the quality of a generation.
Disaster impacts are already at extremely high levels - over the past twenty years, disasters from natural hazards have affected 4.4 billion people, claimed 1.3 million lives and caused $2 trillion in economic losses – and these will worsen by 2030, according to the IPCC SREX report.
Disasters have an overwhelming human, environmental and financial toll on development. This was clearly recognised in The Future we Want document which called for the building of resilience to disasters to be addressed with a renewed sense of urgency in the context of sustainable development.
Therefore, an effective emergency preparedness should be there and able to ensure that rapid, sufficient, and accurate actions are taken in and during disaster.

## Slide 5
Project BACKGROUND Cntd..
Research Project
# Strategic Goal Intosai No 3 :
Encourage SAI cooperation, collaboration, and continuous improvement through knowledge development, knowledge sharing and knowledge services
# Strategic Objective Intosai No 3.2 :
Enable wide exchange of knowledge and experience among INTOSAI members.
# Mandate of KSC:
KSC aims to support greater professionalism and continuous improvement of SAIs by pursuing the following strategic objectives : Enable wide exchange of knowledge and experience among INTOSAI members
INCOSAI XXII Resolve
in Abudabi, 2016
Experience of SAI Indonesia in Carry out of Disaster Audit

## Slide 6: Project OBJECTIVES
01
Identifying community & system preparedness
Step 1
02
Step 2
03
Derive recommendation(s) based on identified problem(s)
Step 3
Providing audit topics & case studies

## Slide 7: RESPONSIBLE SAIs
Project leader
Indonesia
Members
Austria, Bangladesh, Bhutan, Estonia, Guatemala, Iraq, Maldives, Myanmar, Nepal, Philippines, Suriname, Trinidad and Tobago

## Slide 8: 2. PROJECT DESIGN

## Slide 9: The project will emphasize on Auditing Emergency Preparedness, particularly those deal with natural disaster (man-made disaster will be taken into account considerably)
PROJECT
SCOPE

## Slide 10
E
D
C
B
A
Literature Review
Preparing case studies
Drafting (including distributing for comments & finalization)
Study of various countries experiences
FGDs
PLANNED METHODOLOGY

## Slide 11: Project ROADMAP
01
02
03
04
2017
2018
2019
Drafting PID
Distributing PID to KSC & project members
Approval of PID
PROJECT PROPOSAL
Literature studies
FGDs
Preparing case studies
Drafting
RESEARCH & DRAFTING
Distributing draft for comments
Revising draft
Finalization
COMMENTS & FINALISATION
Research project to be approved
FINAL OUTPUT

## Slide 12
No. | Activities | Timeline
1 | First draft of Project Initiation Document (PID) | February 2017
2 | Distributing PID for comments | March 2017
3 | Receiving comments and revising draft PID | March - May 2017
4 | Final version of PID and Approval of PID from KSC | June - July 2017
5 | Meeting of research project group to discuss the Project Plan (TBD) | August 2017
6 | Research, audit, and literature studies to identify the government policies | Sept 2017 – Sept 2018
7 | Reporting of research, audit & literature studies | October 2017 –October 2018
8 | Compiling and drafting the project output (research paper) | November 2018
9 | Meeting of research project group to discuss the draft of Research report(TBD) | December 2018
10 | Distributing Draft of Research Paper for comments | January 2019
11 | Receiving comments and revising draft Research Paper | February – April 2019
12 | Final version of draft research paper | May – June 2019
13 | Report to KSC | August 2019
Detail of Time Frame

## Slide 13: 3. PROGRESS TO DATE

## Slide 14: ACTIVITIES OF THE TEAM
Attended the 9th KSC Meeting in Bali For Presentation of The Project Initiation Document (PID)
Revised the PID Corresponding the KSC Meeting Comments and Thought as a Follows :
Complete the PID with the level of Quality Assurance
Extend the Research Scope not only “Natural Disaster” but also will cover “Man Made Disaster” like Cyber Attack dan Flow of Migration
Accommodate the other Countries' Experiences in Emergency Preparedness policies for Increasing the value of the research.
Using the “Cloud” as Communication Channel among the SAI Members that involved in the Research Project.
Thank you and high appreciation for the members special to SAI Austria, Guatemala and Philippines with your comments and input during the updated of PID.

## Slide 15: FOLLOW UP & PROGRESS
Distribute The Revised PID to KSC and SAI Members on January 2018
Update and attach the Regular Reporting Dashboard as of February and July 2018
Deliver to SAI Members also KSC The “Country Paper Form” For Collecting data and information about Other Countries' Experience in Emergency Preparedness Policies and Activities on March 2018
Analysis the Country Paper Answer on April 2018
Thank You for SAI Guatemala that have sent the Country Paper Answer, We’re still waiting from Other SAI’s Participation.
For SAI Austria with the “Cyber Crime” audit Experiences, we need more information.
We apologize for Cloud and Skype communication models not yet be done
Drafting the Research Project with progress around 45%, but I think the progress still on the track based on the timelines approved in PID.

## Slide 16: DETAIL REPORT OF PROGRESS
No | Outlines of Deliverables | PID | Drafting Process
1.1 | Common phenomenon leading to disasters and their impact |  | 
 | Vulnerabilities and hazards threatening people in the world | √ | √
 | Statistics data of the disaster impact | √ | X
 | Disasters and SDGs | √ | X
1.2 | Concept and definition |  | 
 | Natural and man-made disaster | √ | X
 | Disaster management | √ | √
 | Emergency preparedness | √ | √
 | SDGs | √ | X

## Slide 17: DETAIL REPORT…
No | Outlines of Deliverables | PID | Drafting Process
1.3 | What is needed to cope with disasters |  | 
 | System readiness | √ | √
 | Community based disaster preparedness | √ | √
 | Funding | √ | √
 | Awareness | √ | X
1.4 | Call to action from different stakeholders in alleviating the crisis |  | 
 | Government’s roles | √ | X
 | Other stakeholder’s roles (intermediate agencies, NGOs, private sectors) | √ | X
 | Community’s role | √ | X
 | SAI’s roles | √ | X

## Slide 18: DETAIL REPORT…
No | Outlines of Deliverables | PID | Drafting Process
2.1 | Why prepare for disaster? |  | 
 | Explain the essentials of preparedness rather than emergency response and post recovery | √ | √
 | Coordination between related parties in preparing for any possible disaster | √ | √
 | Mobilization and availability of funding | √ | X
 | International agreements in emergency preparedness | √ | √
2.2 | How Has the Crisis been Responded? |  | 
 | Climate change-related disasters | √ | √
 | Natural disaster | √ | √
 | Cyber-crime | √ | √

## Slide 19: DETAIL REPORT…
No | Outlines of Deliverables | PID | Drafting Process
 | Migration flow | √ | √
 | Nuclear explosion and/or radiation | √ | X
2.3 | The main areas for policy action and recommendations | √ | X
3.1 | Overview of ISSAI in emergency preparedness | √ | √
3.2 | Audit topics on emergency preparedness | √ | X
3.3 | Case studies |  | 
 | Conclusion about efficiency and effectiveness in emergency preparedness which have done by agency and government. | √ | X
 | Conclusion implementations of ISSAI disaster management particularly ISSAI 5510 and new issues as an input of those ISSAIs. | √ | X
Note : √ = Done, X = On Going

## Slide 20: THANK YOU!