## Slide 1: Research Project on Audit Communication and Reporting of Audit Results Presentation on Progress
12 August 2022

## Slide 2: Project Members
1. SAI India (Project Lead) | 
2. SAI Bangladesh | 9. SAI Indonesia
3. SAI Turkey | 10. SAI Italy
4. SAI Kuwait | 11. SAI Costa Rica
5. SAI Hungary | 12. SAI UAE
6. SAI Afghanistan | 13. SAI Mexico
7. SAI Uganda | 14. SAI France (since withdrawn)
8. SAI Suriname | 15. INTOSAI General Secretariat (since withdrawn)

## Slide 3: Chronology of Events…(1)
4th March, 2021: An Introductory Video Conference with KSC Secretariat and Project Team
5th March, 2021: Draft Project Initiation Document (PID) was shared with all Project teams for comments
1st April, 2021: Revised Draft PID was forwarded to the KSC Secretariat
5th April, 2021: KSC Secretariat circulated PID prepared by the project team to members of the KSC Steering Committee for their approval
1st June, 2021: Comments on the PID from Working Groups were forwarded by the KSC Secretariat to the Project Team for comments of the Project Lead

## Slide 4: Chronology of Events…(2)
8th June, 2021: Statement of responses to comments received along with the modified draft PID was forwarded to the KSC Secretariat.
11th August, 2021: KSC Secretariat informed the Project Team of KSC Steering committee’s approval of the Project Proposal on “Audit Communication and Reporting of Audit Results” which is placed at level 2 of QA Protocol.
17th August, 2021: Project Lead informed the Team of approval of the PID and shared that the team from SAI India had almost finalized the draft Preliminary Survey for collecting basic information from SAIs, which would be shortly shared with the entire Project Team.

## Slide 5: Chronology of Events…(3)
14th September, 2021
  Preliminary Survey Form and the Draft format of the Project Report were shared with the Project Team
  Project Lead sought inputs on the kind of participants (other than SAIs) to whom the final Survey forms could be shared with, as part of this Project
  The filled-in Survey form was requested to be shared with the Project Lead positively by 30 September, 2021.
  Only one response (SAI Kuwait) was received by 30 September, 2021
  Six other responses received between 1 Oct 2021 and 14 February 2022
23rd October, 2021
  Email from the Project Lead requesting responses from all members of the Project Team.

## Slide 6: Chronology of Events…(4)
2nd December, 2021 :Questionnaire-2 (containing SAI specific queries) and Chapter-wise suggestive aspects along with distribution of work were emailed to the Team
  Following timelines were proposed to complete the task of preparing the initial draft of the Project Report as per PID timeline for Exposure Draft:
(a) preparation of contents as per attached distribution of work, to be
completed by 31 December 2021
(b) review of contents by 15 January 2022
(c) finalization of draft contents by 15 February 2022

## Slide 7: Chronology of Events…(5)
17th January, 2022 :
  Project Lead informed the team by email that consolidated documents have been uploaded in the INTOSAI Community Portal (Community of Practice : Research Project on Audit Communication)
  Members were requested to communicate their (i) plan of action, (ii) timelines and (iii) commitments to provide the filled-in Preliminary Survey Form, Questionnaire-2 and respective portions of the first draft as per the distribution of work by 24 January 2022.
  As of date, contributions to the draft have been received from SAI Italy and SAI UAE only.
2nd February, 2022 :
  The Project Lead proposed to conduct a VC on 07 February 2022 (at 6.00 pm Indian Standard Time) with all members of the Project Team
    to assess the overall status of the Project
    to identify possible constraints and solicit suggestions to overcome them
    to seek suggestions to take the Project forward
    Due to limited response, the VC could not be held

## Slide 8: Chronology of Events…(6)
27th April 2022
  Project team members were requested to communicate within one week, i.e by 04 May 2022, a timeline for completing the pending commitments.
  Members were also requested to share with us if they have any constraints or limitations in contributing to this Research Project, by 04 May 2022. However, till date, only SAI Turkey has responded to this request.
23rd May 2022
  Two threads had been created in the Community of Practice for Preliminary Survey and Questionnaire 2 and all responses to these surveys had been uploaded in the relevant threads.
12th August 2022
  Given the above limitations of material, the survey questionnaires have been shared with SAIs outside the Project team. This has become essential to reduce dependence on open source material for this Project. SAIs have been requested to provide responses by 11 September 2022.

## Slide 9: Quality Assurance Process
QA level identified for the Project is Non-IFPP QA Level 2
Approved PID envisaged engagement of and consultation with other SAIs outside the project team/External bodies/academic institutions
Due to limited response from the Project Team, the Preliminary Survey and Questionnaire-2 have been circulated to the larger INTOSAI Community. Responses received, as and when, will be incorporated in the Draft report.
The quality assurance would need to factor the information/responses received from these SAIs as well. Thereby, the process would need further assistance of the SAIs participating in the Project Team, towards building the first draft and supporting the Project Lead in the journey towards ensuring that the Project meets its designated objectives, as enshrined in the approved PID. Commitment in this regard will be required to be solicited from the Project team members.

## Slide 10: Preliminary Survey Form : Responses
SAI Turkey
SAI UAE
SAI Kuwait
INTOSAI General Secretariat
SAI Mexico
SAI Costa Rica
SAI Hungary

## Slide 11: Questionnaire-2 : Responses
SAI UAE
SAI Kuwait
SAI Turkey

## Slide 12: Shift of Project Timelines…(1)
Milestone/Activity | As per Approved PID | Status of work | Proposed timelines
Approval of PID | April 2021 | August 2021-DONE | -
Circulation of Survey Matrix to stakeholders (Circulation of Questionnaire-2 to stakeholders) | June 2021 | September 2021-DONE December 2021-DONE | -
Receipt of response to the circulated Survey Matrix Receipt of response to Questionnaire-2 | August 2021 | 7 partial responses received till date 3 partial responses received till date | -
Sharing of first exposure draft among project team members Communication of timelines by when commitments would be met Sharing of Resource Material for the Project Sharing of Responses to Surveys among the Team | September 2021 | Yet to be achieved One response received December 2022-DONE May 2022 - DONE | 30 November 2022 subject to sufficient responses

## Slide 13: Shift of Project Timelines…(2)
Milestone/Activity | As per Approved PID | Status of work | Proposed timelines
Sharing of second exposure draft among project team members and after finalizing seek approval of KSC Steering Committee on the exposure draft | November 2021 | Yet to be achieved | January 2023
Exposure of Draft | 01 Feb’22 – 31 Mar’22 | Yet to commence | 01 April 2023 – 30 May 2023
Circulation of draft endorsement version among project team members | May 2022 | -- | July 2023
Forwarding of Final draft along with action taken statement, to KSC Secretariat for seeking approval of the Steering Committee | June 2022 | -- | August 2023

## Slide 14
THANK YOU