## Slide 1: Agenda Item 10 KSC Work Plan 2020-22
SAI-India
11th Meeting of KSC Steering Committee
Pampanga, Philippines
(12-14 June 2019)

## Slide 2: Mandate of KSC
Encourage SAI cooperation, collaboration, and continuous improvement through knowledge development, knowledge sharing and knowledge services, including producing/revising INTOSAI products, providing benchmarks, operating community portal, conducting best practice studies, and performing research on issues of mutual interest and concern.

## Slide 3: Strategic Objectives for Goal 3
INTOSAI Strategic Plan 2017-22 defines following three objectives for KSC
Develop international expertise in the various fields of public-sector auditing and provide content to INTOSAI’s framework of professional standards
  Enable wide exchange of knowledge and experience among INTOSAI members.
  Working with the CBC, IDI, and other INTOSAI entities, facilitate continuous improvement of SAIs through knowledge sharing on the crosscutting lessons learned from the results of peer reviews and SAI PMF.
And five Crosscutting Priorities of INTOSAI:
  Advocating for and supporting the independence of SAIs
  Contributing to the follow-up and review of the SDGs
  Ensuring effective development and coordination among standards-setting, capacity development, and knowledge sharing
  Creating a strategic and agile INTOSAI
  Building upon, leveraging, and facilitating cooperation and professionalism among the regional organizations of INTOSAI

## Slide 4: Key Strategies to achieve the Objectives
Preparation of new INTOSAI products (1) Revision of INTOSAI products (2) | INTOSAI Community Portal (3) Research Projects and engagement with Academic Institutions (4) Generation and dissemination of Knowledge and experience (8) | Stakeholder engagement (5) Lessons learned from SAI PMF and Peer Review (6) Cooperate with the International Journal and the General Secretariat to expand use of real-time communication tools (7)
Knowledge Development | Knowledge Services | Continuous Improvement

## Slide 5: Activities undertaken in Work Plan 2017-19
Sl | Strategies | Status
1 | Preparation of new INTOSAI products and product lines | IFPP KNI - likely to be completed by XXIII INCOSAI Jurisdictional SAIs - likely to be completed by XXIII INCOSAI Public Procurement Audit – likely to completed by 2020 GB Non-IFPP All 27 products are expected to be completed by XXIII INCOSAI.
2 | Revision of ISSAI products | IFPP IT Audit likely to be completed by XXIII INCOSAI Privatisation likely to be completed by 2020 INTOSAI GB Public Debt likely to be completed by 2020 INTOSAI GB. Disaster Related aid likely to be completed by 2020 INTOSAI GB
3 | INTOSAI KSC-IDI Community Portal | Migration of the WG pages be completed in KSC Work Plan 2017-19
4 | Research projects and engagement with the academic community | “Auditing Emergency Preparedness” to be completed by XXIII INCOSAI. “ Citizen Participation in Public Audit” will be completed in 2020 before INTOSAI GB.

## Slide 6: Activities undertaken in Work Plan 2017-19 (contd.)
Sl | Strategies | Status
5 | Stakeholder engagement | Activities envisaged in terms of meetings, workshops, seminars completed. WGs have been engaged in setting up working relationship with various external stakeholders within their domain
6 | Lessons learned from SAI PMF and Peer Review | Peer Review Work Stream has coordinated and collected information on peer reviews conducted. The details of lessons learned are being complied by the Work Stream.
7 | Cooperate with and leverage the efforts of the International Journal of and the General Secretariat | WG have engaged with the Journal and INTOSAI General Secretariat in their activities.
8 | Generation and dissemination knowledge and experiences. | Dissemination activities undertaken through WG seminars, trainings and workshops as envisaged in the WGs’ Work Plan.

## Slide 7: Activities proposed for Work Plan 2020-22
Sl | Strategies | Proposed Activities
1 | Preparation of new INTOSAI products and product lines | Activity 1: 11 new non-IFPP products planned by 4 WGs IFPP projects in alignment with SDP after finalization by PSC All Working Groups to share planned products before INCOSAI 2019 for addition to this Work Plan.
2 | Revision of ISSAI products | WGs to review all existing knowledge products developed outside the ISSAI framework and QA principles for continuing applicability
3 | INTOSAI KSC-IDI Community Portal | Activity 2: Content enrichment and updation of pages of each Working Group in the Community Portal. Active participation of the Working Groups project teams in usage of real-time features of the Portal Actively promote the Portal beyond project group members to member SAIs in Working Groups.

## Slide 8: Activities proposed for Work Plan 2020-22
Sl | Strategies | Proposed Activities
4 | Research projects and engagement with academic community | Activity 3: Research (a) SAI Independence (b) Audit communications and Reporting of Audit Results. Activity 4: All WG Project teams and Research teams be encouraged to identify subject-specific professional bodies and academic institutions and engage with them during conception and drafting of project documents
5 | Stakeholder engagement | Activity 5: Increased cooperation and engagement with Regions in the activities of KSC and Working Group activities. Working Group chairs to represent KSC in Regional Organisations’ meetings to seek support and actively engage in KSC and Working Groups activities. Strengthen engagement with PSC, CBC, PFAC, SCEI, IDI and INTOSAI General Secretariat

## Slide 9: Activities proposed for Work Plan 2020-22
Sl | Strategies | Proposed Activities
6 | Lessons learned from SAI PMF and Peer Review | Activity 6: Peer Review Work Stream to bring out a compendium on the peer review results and lessons learned in 2021. KSC will engage with the Peer Review Work Stream to understand and disseminate the lessons learned through INTOSAI Community Portal.
7 | Cooperate with and leverage efforts of International Journal of and General Secretariat to expand use of real-time communication tools | Activity 7: Greater usage of webcasting, VC and Q&A tools by the General Secretariat and the INTOSAI Journal body to disseminate their products , along with enrichment of library resources to facilitate meaningful cooperation
8 | Generation and dissemination of knowledge and experiences. | Activity 8: WGs activities are geared towards collecting, sharing and creating new knowledge in their field More efforts by WGs to identify good practices in subject domain and sharing these practices through case studies and blogs on the Portal.

## Slide 10: Crosscutting Priorities of INTOSAI
To use INTOSAI Community Portal to disseminate information relating to SAI Independence.
Collaborate with IDI on Audit of Implementation of SDGs. The Working Groups will also continue to engage and contribute towards SDGs.
  Create a Communities of Practice on audit of SDGs.
Continue the collaborative effort with other Goal Chairs.
Continue to participate in SCEI activities and use the INTOSAI Community Portal to gather information on new emerging areas in public auditing and associated risk.

## Slide 11: Performance Indicators for assessment of Strategic Objectives for KSC
Challenging task as the indicators for most activities will be in the nature of output indicators ( Number of products developed, number of research papers published etc.)
Difficult to use outcome or impact indicators as the outcome and impact in many cases would depend upon the extent to which the products/research papers are actually put to use by the SAIs
Survey result, though a soft indicator, seems to be the only viable option to measure SAIs satisfaction with KSC work.
Since the activities of KSC are mainly undertaken through its Working Groups, the WGs may individually carry out survey on the performance of their activities.
Send the results to KSC Secretariat for consolidation into Performance report of KSC and for prioritizing action items.

## Slide 12: Resources
Goal Chair allocation
In-kind contribution. Working Groups encouraged to expand such support from the SAI community during this Work-Plan as well.

## Slide 13: THANK YOU

## Slide 14: List of activities
1. Revision and Preparation of new INTOSAI products
1.1 Follow up on the Projects under SDP 2017-19 of IFPP.
1.2 Support initiatives proposed to be undertaken in the SDP 2020-22.
1.3 Review all existing products developed outside the erstwhile ISSAI framework and align them with QA principles.
2. KSC Knowledge Sharing Platform
2.1 Migrate and update webpages of the Working Groups in the Community Portal.
2.2 Active participation of the Working Groups in maintaining a robust Portal and using the various facilities like Communities of Practice, Video Conferencing, Webinar etc. in their activities.
2.3 Actively promote the Portal among the Working Groups members and within their SAIs.

## Slide 15: List of activities
3. Research projects
3.1 Carry out crosscutting research projects on “SAI Independence” and Audit Communication and Reporting of Audit results”
3.2 Involve all members of the Steering Committee in the two projects.
4. Engagement with Academic communities
4.1 Actively engage professionals from major academic institutions, research institutions and professional associations in the Working Group activities.
5. Stakeholder engagement
5.1 Increased cooperation and engagement with Regions in the activities of KSC and Working Group activities.
5.2 Working Group Chairs to represent KSC in Regional Organisations’ meetings to seek support and actively engage in KSC and Working Groups activities.
5.3 Strengthen engagement with PSC, CBC, PFAC, SCEI, IDI and INTOSAI General Secretariat.

## Slide 16: List of activities
Facilitate continuous improvement
6.1 Continue consultations with Peer Review Work stream and IDI SAI PMF unit and disseminate the lessons learnt in INTOSAI Community Portal.
7. Cooperate with INTOSAI Journal and General Secretariat
7.1 KSC Secretariat and Working Groups will continue to cooperate and leverage the efforts of the INTOSAI Journal of Government Auditing and the General Secretariat.
8. Generation and dissemination of Knowledge and experience
8.1 Working Groups will strive to ensure that the activities are geared towards collecting, sharing and creating new knowledge in their field and disseminating the best practices among SAIs to upgrade accountability and governance in their respective countries.

## Slide 17: List of activities
9. Crosscutting Priorities of INTOSAI
9.1 To use INTOSAI Community Portal to disseminate information relating to SAI Independence.
9.2 Continue to participate in SCEI activities and use the INTOSAI Community Portal to gather information on new emerging areas in public auditing and associated risk.
9.3 Continue the collaborative effort with other Goal Chairs.
9.4 Collaborate with IDI on Audit of Implementation of SDGs. The Working Groups will also continue to engage and contribute towards SDGs.
9.5 Create a Communities of Practice in the INTOSAI Community Portal to promote and facilitate exchange of knowledge on audit of SDGs

## Slide 18: Non-IFPP knowledge projects - Work-Plan 2020-22
WG | Proposed Knowledge projects
WGITA | Cybersecurity/Data Protection Audit of IT management Functions Performance Evaluation of IT Systems
WGPD | Mapping of relevant provisions of Public Debt ISSAIs for development of non-IFPP guidance material Fiscal Exposure Guideline on audit of Government Guarantees.
WGEA Draft plan | Auditing Plastic Waste Auditing Climate financing Auditing Sustainable Transport
WGBD Draft plan | Guideline on Data analytics Research for Auditing Technologies Innovation

## Slide 19: Selection of Research projects
Four topics were shortlisted based on FIPP Scanning document, SCEI report and the last KSC Work Plan survey results.
This was followed by a Survey to ascertain members’ interest in participating in these projects.
29 SAIs and IDI responded to the survey.
Five SAIs did not offer any comments.
Proposed additional topics could be considered for Research Projects under next Plan.
Steering Committee member SAIs to be members of both research groups. External stakeholder consultation would be part of the methodology