## Slide 1: Agenda Item 2 Highlights from the KSC Reporting Dashboard
INTOSAI Knowledge Sharing and Knowledge Services Committee

## Slide 2: SDP 2017-19: Status of Projects
IFPP Projects
  7 projects- coordinated by KSC
    3 projects -New Pronouncements
    4 projects -Consolidating 18 ISSAIs from old ISSAI framework

## Slide 3: SDP 2017-19: Status of Projects
3 New Pronouncements
  Endorsed in XXIII INCOSAI
    Principle P-50 on Jurisdictional Activities of SAIs (SAI France)
    GUID on Key National Indicators (SAI Russia)
  Aimed for completion by 2021 INTOSAI GB
    GUID on Public Procurement Audit (SAI Russia)

## Slide 4: SDP 2017-19: Status of Projects
6 new GUIDs - Consolidating 18 ISSAIs in old framework
  Endorsed in XXIII INCOSAI
    GUID on IT Audit (SAI India)
  For approval at 2020 GB
    GUID on Audit of Public Debt (SAI Philippines)
  Aimed for completion by 2021 INTOSAI GB
    GUID on IT Security Audit (SAI India)
    GUID on audit of Privatisation (SAI India)
    GUID on audit of Public Private Partnership (Ecuador)
    GUID on audit of Disaster Related Aid (ECA)

## Slide 5: Work Plan 2017-19: Status of projects
Non-IFPP Products
15 Products were endorsed in the XXIII INCOSAI
  3 Guidance and 6 Research Papers- WGEA (SAI Indonesia)
  2 Guidance –WGITA (SAI India)
  2 Research Papers-WGVBS (SAI Mexico)
  1 Briefing Note and 1 Training Framework- WGEI (SAI Uganda)

## Slide 6: Work Plan 2017-19: Status of projects
Non-IFPP Products
12 products are at various levels of completion under QA Process
  3 Guidance WGVBS (SAI Mexico)
  5 Guidance – WGFACML (SAI Egypt)
  1 Guidance -WG SDG KSDI (SAI Russia)
  2 Guidance, -WGBD (SAI China)
  1 Framework and auditor’s toolkit- WGEI (SAI Uganda)

## Slide 7: Work Plan 2017-19: Status of projects
KSC Research Projects
  Endorsed in the XXIII INCOSAI
    Disaster Preparedness for Supreme Audit Institutions (SAI Indonesia)
  Proposed to be withdrawn
    Citizen Participation in Public Audit (SAI Guatemala) - Experiencing considerable delays due to constraint of resource persons

## Slide 8: SDP 2020-22 IFPP
2 project proposals forwarded to FIPP for examination-under component 2
    Guidance for implementing INTOSAI-P 50 Principles - Forum for Jurisdictional Activities (SAI France)
    Guidance on Cooperation between SAIs and three branches; Legislature, Judiciary, and Executive - WGVBS (SAI Mexico).
  Aimed for XXIV INCOSAI in 2022

## Slide 9: Work Plan 2020-22 Non-IFPP
  12 Guidance and research materials
    4 Guidance- WGEA (SAI Finland)
    3 Guidance -WGITA (SAI India)
    3 Guidance and 1 Mapping document- WGPD (SAI Philipines)
    1 GuidanceWGBD (SAI China)
  Proposal on assessing the implications of rising public debt as a result of the COVID-19 is under examination by the WGPD

## Slide 10: Work Plan 2020-22 Non-IFPP
2 KSC Research Projects
  SAI Independence (SAI France) – Project proposal presented for approval at this KSC SC meering.
    Members: Afghanistan, Austria, Bangladesh, Bhutan, France, Germany, Guatemala, IDI, Indonesia,, India, Italy, Suriname, Turkey, Vatican City.
  Audit Communication and Reporting of Audit Results - Project lead being identified
    Members: Afghanistan, Austria, Bangladesh, Costa Rica, France, Hungary, Indonesia, India, Italy, Kuwait, Mexico, Suriname, Turkey, Uganda,

## Slide 11: KSC Research Projects
Quality Assurance procedure for products developed outside the Due Process
Both research projects targeted for completion before XXIV INCOSAI.

## Slide 12: Knowledge Sharing Activities
New Working Groups
2 Working Groups created in XXIII INCOSAI
  Working Group on Impact of Science and Technology on Auditing
    Chair: SAI UAE & Vice Chair: SAI USA
  Working Group on SDGs and Key Sustainable Development Indicators
    Chair: SAI Russia
    sucessor to the earlier Working Group on Key National Indicators

## Slide 13: Knowledge Sharing Activities
Working Groups continuing with their knowledge dissemination activities.
Due to COVID-19 pandemic, Working Groups adopted online platforms for holding their annual meetings.
Utilized facility in INTOSAI Community Portal [WGITA, WGEI]

## Slide 14: Knowledge Sharing Activities
Modes and technologies
  Twitter
    WGEA , WG SDG KSDI
  MOOC
    WGEA
  Webinars
    WGITA , WGPD
  Training Tool Kits
    WGEA, WGEI
  Newsletters
    WGEA , WGEI , WGFACML, WG SDG KSDI

## Slide 15: Partnering with IDI
KSC & IDI
IDI KSC Cooperative audit programme on Preparedness for implementation of SDG
  73 SAIs & 1 Sub-national audit office
  KSC-IDI publication “Are Nations Prepared for Implementation of SDGs?”
  Guidance on Auditing Preparedness for Implementation of SDGs.
KSC partnering with IDI and Regions
  Cooperative audit of strong and resilient national public health systems [3.d Audit]

## Slide 16: Partnering with IDI
Working Groups & IDI
  WGPD - Development and co-branding of the Handbook on Audit of Public Debt: A Guide for Auditors.
  WGITA - Development of IT Audit Handbook.
  WGEA - Audit of Disaster Management.
  WGFACML - Programme on SAIs Fighting Corruption
  WGSDG KSDI- Training Courses on SDGs auditing

## Slide 17: Goal Chair Collaboration
Since 2014,
Chairs Goals 1, 2 and 3 collaborated more closely and more regularly
Collaboration helped in effective coordination
interlinked activities
facilitate achievement of individual goals and ambitions.

## Slide 18: Goal Chair Collaboration
INTOSAI Strategic Plan 2017-19 enhanced this collaboration and coordination as a cross-cutting priority.
Collaborative initiatives include
  Governance of FIPP
  SDPs of IFPP,
  QA on Global Public goods outside IFPP
  Setting of Technical Support Function
  Work related to professionalism of SAI auditors

## Slide 19: Goal Chair Collaboration - Future
Elaboration of INTOSAI Strategic Plan 2023–2028.
Working on integrating towards a single “strategic plan for all professional matters of INTOSAI”.
  Leveraging INTOSAI’s resources in an efficient and effective way
  Provide SAIs with high quality professional support to meet their needs

## Slide 20
Thank you