## Slide 1: Agenda Item 3 Progress of INTOSAI Strategic Plan (2023-28)
INTOSAI Knowledge Sharing and Knowledge Services Committee

## Slide 2: Task Force on Strategic Planning
Re-established by 72nd GB in 2019
  To develop the strategic plan for the period 2023-28.
  Task Force is Chaired by SAI USA.
Internal & External Scan survey to gather inputs
  Understand existing strengths, challenges, opportunities, and emerging issues

## Slide 3: Aimed Timelines
Task | Period
TFSP Survey Administration | September –November 2020
Summarize and share results of Internal & External Scan finding with INTOSAI members | January – April 2021
Share draft Strategic goal plans, activities and objectives with INTOSAI members for initial review | May-June 2021
INTOSAI TFSP meeting | June 2021
Share draft of Strategic Plan with all INTOSAI members | March 2022
Issue final draft Strategic Plan 2023-28 | September 2022

## Slide 4: Expectations from Working Groups
Actively participate in the TFSP survey process
Encouraging Working Group members to provide their inputs.
KSC Secretariat is also considering to float an additional survey
  To gauge the satisfaction and seek suggestions for KSC deliveries.
  Add to the Internal scan of TFSP in the formulation of the next Strategic Plan.
  Contribute in formulation of survey questions
  Actively participate in the KSC survey

## Slide 5
Thank you