## Sheet1
Enterprise Risk Management of KSC
Strategic Objective of KSC | Strategies | Risks | Assess Risks: Likelihood | Assess Risks: Impact | Risk response
3.1 Maintain expertise in the various fields of public-sector auditing and help to provide content to INTOSAI’s framework of professional standards for consideration by the Common Forum | 3.1.1 New INTOSAI products developed | IFPP overloaded with several new GUIDs | Requests have already been received from several Working Groups to revise the Strategic Development Plan of IFPP to include new projects for developing GUIDs. So, the risk is real. | IFPP will become unwieldy. Significant resources may be invested in developing new products which may not be put to much use by the INTOSAI Community resulting in poor value for money for the efforts. Also, it may place undue workload on FIPP and could compromise the quality of review work by FIPP. | KSC Chair has already had telephonic/video conferences with the Working Groups and explained the risks of overloading the IFPP. The number of proposals for new IFPP documents has already been reduced significantly through continuous dialogue with the Working Groups.
|  | Projects may not get completed in a timely manner | As per the Project proposal, FIPP requires 9 months for approval at various stages and mandatory 90 days have to be provided for the exposure, leaving only 12 months for the development/revision of the pronouncement. The risk is low as in the past, most of the projects for development of new products have been completed and INCOSAI approval obtained as planned. However, there have been one/two projects that could not be completed as planned and challenges have also been noticed in completing translations. | New products that are in the verge of completion may have to wait for three more years before approval at the next INCOSAI. | All projects would now be part of the SDP of IFPP and monitored by the Goal Chair as well as by FIPP.
| 3.1.2 ISSAI products revised | Difficult to organize resources to undertake revision of products that were developed by dissolved Working Groups (e.g. Audit of Privatization and Audit of Disaster related aid) | The goal chairs may not find required resources to review the products. Further, we have experienced difficulties in completing revision of ISSAIs of disbanded working groups in the last 2-3 years. So, the risk is real. | IFPP products would not be revised as per agreed maintenance cycle and may lose relevance. | KSC Chair working with FIPP has already devised a mechanism to identify a preliminary team to carry out work on the need for the revision of the documents before proceeding with revision exercise.
|  | Revision may not get completed in timely manner | As per the Project proposal, FIPP' requires 9 months for approval at various stages and mandatory 90 days have to be provided for the exposure, leaving only 12 months for the development/revision of the pronouncement. Because of the detailed project proposal which also includes timelines, the risk is low. | New products that are in the verge of completion may have to wait for three more years before approval at the next INCOSAI. | All projects would now be part of the SDP of IFPP and monitored by the Goal Chair as well as by FIPP.
| 3.1.3 Other than ISSAI products developed | Overload of Non-IFPP Documents | Stern requirement to include the Projects in SDP and the constraints of FIPP may lead to many non-IFPP documents. The risk is high. | Significant resources may be invested in developing new products which may not be put to much use by the INTOSAI Community resulting in poor value for money for the efforts. The initiatives are mainly driven by the working groups and may not necessarily be based on a prioritization of members’ needs | WGs will be advised to take up limited projects for development of non-IFPP documents by prioritizing needs. WGs will also be asked to periodically review and weed out unwanted documents.
|  | Quality assurance of non-IFPP Documents | Non-IFPP documents may not follow the required Due Process and therefore the quality of the document is not assured. From the past experience, the risk is high | Poor quality of non-IFPP documents | A joint paper to assure quality of Non-IFPP documents as in the case of IFPP documents has been drafted by the three Goal Chairs in consultation with IDI. A Proposal of adding Quality Assurance Statement with a expiry/review clause signed by Goal Chairs mentioning the extent of follow up of the Due Process is being proposed for endorsement in the GB.
3.2 Enable wide exchange of knowledge and experience among INTOSAI members | 3.2.1 Utilization of INTOSAI Community Portal | INTOSAI Community Portal not being used. | The risk is high as the INTOSAI Collaboration Tool which was a precursor to the portal was not put to good use. | We may lose one of the best sharing and communicating platform developed only for INTOSAI Community. | The KSC Portal is being revamped to add additional features like multilingual support, portability and ease of use. The WGs and Research Teams would be encouraged to use CoP and spread the word on the benefits of the Portal. All the working groups of KSC are being requested to use the portal as their webpage so that there is a single window access.
| 3.2.2 Utilization of websites of WGs and TFs of KSC | Websites not developed or not put to use. | As some Working groups are yet to have their own websites, the risk is real. | Severely impact knowledge sharing objective. | The revamped Portal will have separate web pages for each WG/TF of KSC. Thus even WGs without their own website can have a page in the Portal. As access will be through a single window, use of websites is expected to increase.
| 3.2.3 Finalization of research reports on topics of mutual interest and concern of INTOSAI fraternity | Not enough participation from the member SAIs in the Research Projects | Most of SAIs are yet to forward the details of their representatives in the project. The risk is real. | The research document may not be comprehensive and representative of the INTOSAI Community. | SAIs will be encouraged to participate in the research projects. The project proposal could also includes survey to gather information pertaining to the subject matter from as many SAIs as possible. SAIs would be encouraged to contribute towards this exercise.
|  | The Quality and value addtion of the Research papers may not be satisfactory. | Since this would not be treated as IFPP Document, the process to be followed for quality assurance is required to be determined. The risk is high. | Reputation risk to KSC and INTOSAI due to poor quality of research documents. | Quality assurance for non-IFPP document should tackle the quality issue. The Research Project leads will be asked to engage wider INTOSAI Community and bring varied experiences and perspectives that would be of value.
| 3.2.4 Implementation of IDI-KSC programme on Auditing Preparedness for implementation of SDGs | Since IDI is main implementating agency of the programme, IDI Risk assessment on the programme may be referred to.
| 3.2.5 Enhanced cooperation with INTOSAI Regions | Mechanism for cooperation may not evolve. KSC will not be in a position to leverage the Regions experience and support in disseminating the INTOSAI's knowledge across diverse geographical and cultural context. | Non-participation of Regions in the KSC Steering Committee meetings. The risk is real. | One of the core functions of KSC is gathering and disseminating of knowledge and experience. Without the support of regions, KSC may not able to to reach out to the smallest and remotest of SAIs who have little exposure to big INTOSAI events. | Interaction of Goal chairs with all the regions a day before GB is being explored.
| 3.2.6 Establishment of cooperation with academic institutions/ universities | Non-cooperation from the academic institutions. | Area of cooperation and yardstick to pick the institution has not been defined. Further, they may not be too many takers. Financial implication, if any has to be worked out. The risk is real. | Absence of meaningful cooperation and dialogue with academic institutions. | Steering committee meeting will discuss on the yardstick for selection of Universities and the areas of cooperation that would benefit INTOSAI. The financial implications on these collaboration, if any, may also have to be addressed.
| 3.2.7 Use WGs , TF and Communities of practice open to all interested SAIs as vehicles for generating and disseminating knowledge and experience | The various activities like training, workshops, joint/cooperative audits etc. as envisaged by the WGs in their work plans may not take place | Likelihood of the risk is quite low, due to monitoring of the activities by Steering Committee and the Goal chairs. Though the performance measurement for some activities may be lacking. | The desired objective of developing and disseminating the knowledge may not be achieved. | A robust reporting dash board is being devised to monitor/measure the progress of the activities and to take remedial actions. The steering committee/Goal chairs will take appropriate steps to provide the required direction to the WGs.
3.3 Working with CBC, facilitate continuous improvement of SAIs through knowledge sharing on the crosscutting lessons learned from the results of peer reviews and SAI PMF | 3.3.1 Disseminate compilation of crosscutting lessons learnt on Peer Reviews and SAI PMF | Mechanism for cooperation may not evolve | The feedback from the concerned work streams is vital to accomplish this goal. The risk is low. | Use of KSC mechanism in disseminating of knowledge and experience on the assessment tools like peer reviews and SAI PMF, may be hampered. | Talks have been held with CBC to evolve a mechanism to achieve this objective. A three way consultation between the chairs of the Peer review and SAI PMF works streams, IDI SAI PMF unit and the chairs of Goal 2 and 3 is being explored.
Crosscutting Priorities
CP-1: Contribution towards Advocating for and supporting the independence of SAIs |  | Swift and coordinated action which is needed from the INTOSAI General Secretariat and Regional Secretariat to support SAIs whose independence has been compromised by executive/ legislative action, may not be forthcoming. | The risk probability is not likely to be high, but it is an obvious risk. | Affected SAI may not get the necessary support from the international public sector sector audit community. | A Standard Operating Procedure (SOP), if not already available, may be needed for the INTOSAI and Regional Secretariat to respond when SAIs independence are adversely affected by legislative/executive action of national government.
|  | Lack of support to SAIs that do not have sufficient independence | Several initiatives (project led by SAI of Austria, IDI's programme on SAI Independence etc) are being taken to support SAIs. So, the risk is low. | SAIs may not get the necessary support and expertise needed to tackle the independence issue. | As KSC is concerned with Knowledge Sharing and Services, we have created a separate folder in the Library in the INTOSAI Community Portal on SAI Independence and this various documents, including independence assessment toolkits. This is expected to create greater awareness and sharing of good practices on independence.
CP-2 : Contributing to the follow-up and review for the SDGs within the Context of each nation's specific sustainable development efforts and SAIs individual mandates. |  | The programme objectives of IDI-KSC cooperative audit programme on auditing preparedness to implement SDG may not be achieved. | Since IDI is main implementating agency of the programme, IDI Risk assessment on the programme may be referred to.
|  | Member SAIs are ignorant about the various development under 4 approaches on SDG and expectations from them. | The risk probability is not likely to be high, but it is an obvious risk. | Due to ignorance and non-dessimination of information INTOSAI may not be an effective contributor to the success of SDG implementation. | KSC has been identified as the hub for INTOSAI efforts to share knowledge on SDG. KSC-IDI Community Portal can be used as an effective tool to be a single window for sharing of knowledge and information on latest happenings on SDG in the INTOSAI.
CP-3: Ensuring effective development and coordination among standards-setting, capacity development, and knowledge sharing to support SAIs and improve their performance and effectiveness. (*) |  | Lack of coordination may lead to duplication, inconsistency or gaps in INTOSAI efforts in supporting SAIs to improve their performance and effectiveness. | The risk is quite low in view of the significant efforts made in the last 2-3 years for Goal Chairs collaboration. | As standards setting, capacity development, knowledge sharing and assessment tools are part of a value chain, lack of coordination among the Goal Chairs may cause a break in the value chain resulting in low value for money for the resources deployed by the three Goal Chairs and the sub-committees, working groups and workstreams under them. | As there is effective collaboration among the goal chairs already, no further action is needed.
CP-4: Contributing to creating a strategic and agile INTOSAI that is alert to and capable of responding to emerging international opportunities and Risk |  | Supervisory Committee on Emerging Issues (SCEI) does not have a proper medium to communicate with and get inputs on latest developments from INTOSAI members. | SCEI does not have any website of its own, therefore, the risk is real | INTOSAI members may not be aware of the work done by SCEI. Further, INTOSAI members may not be able to provide timely inputs on emerging issues that would be vital for the success of SCEI. | KSC would provide in its KSC Community Portal, a Community of Practice, a forum for interaction between SCEI members and also a tool to get inputs from INTOSAI members on emerging developments of interest to INTOSAI.
CP-5: Building upon, leveraging and facilitating cooperation and professionalism among the regional organisations of INTOSAI. |  | As Regional organizations are independent entities, cooperation between INTOSAI and the regions may be ineffective. | Risk is high as regional entities have a strong identity of their own and their work may not be aligned with INTOSAI. | As regional entities are the closest to the SAIs and as regional entities are the vehicles to disseminate and deliver INTOSAI products, absence of professional resources in the regional entities may adversely affect the INTOSAI efforts to build capacity and strengthen propfessionalism of the SAIs. | The latest plan to dedicate a day before the INTOSAI GB to interact with the regions is a positive development that could mitigate the risk.
(*) The risk on this Crosscutting priority is being discussed with other Goal Chairs. This may undergo revision.