## Slide 1: Citizen Participation in Public Audit
INTOSAI Knowledge Sharing Committee (KSC)
Presentation
23 August 2017
Notes: Good Afternoon to all INTOSAI members
Today the we will be presenting the Research Project on the “Citizen Participation in Public Audit”.
This presentation is based on the 3rd Draft of the Project Initiation Document which is a collaborative effort of SAI Guatemala and SAI Philippines. The draft has been submitted to KSC and we have included the comments given by KSC in the 3rd draft.

## Slide 2: Background
Significant Steps taken by SAIs:
Fight corruption
Promoting transparency
Maintaining efficient and effective government control systems
Enhancing accountability systems
Offering governance processes for the benefit of society through the involvement of citizens
Notes: Citizen Engagement is not new. Early works were quite inspirational for many of us who have worked on issues of gathering and acting on citizen feedback.
At the same time, something important has changed. There has been an increasing demand by civil society and citizens to have a greater say in public decision-making, and a desire among many governments to be more inclusive and responsive to citizens’ needs. The rise of innovations in technology has provided citizens with new and unprecedented opportunities to directly engage policy makers and demonstrated the potential to facilitate “Closing the Feedback Loop” between citizen and governments.
To address this need, the audit processes carried out by several SAIs have taken significant steps to:
(Source: World Economic Forum – 10 lessons on Citizen Engagement https://www.weforum.org/agenda/2016/01/10-lessons-on-citizen-engagement)

## Slide 3: Background
ISSAI 12:
                “The Value and Benefit of
                Supreme Audit Institutions –
                making a difference
                in the lives of Citizens”
Notes: The partnership between SAIs and citizens/civil society organizations is also in conjunction with ISSAI 12:
“The Value and Benefit of Supreme Audit Institutions – making a difference in the lives of Citizens”

## Slide 4: Various Models of Citizen Participation
SAI Korea’s Policy Advisory Committee and Advisory Groups
    Civil Petitions Reception
    Citizen Auditor System
  SAI India’s social audit model
SAI Honduras model of conducting public meetings
SAI USA’s model of engaging the National Academy of Sciences
SAI Philippines’ model of citizen participatory audit
Notes: Here are the various models of citizen participation adopted by some SAIs:
SAI Korea’s Policy Advisory Committee and Advisory Groups comprised of experts from all walks of life primarily professors or representatives of respected research institutions, that offer advice on the SAIs audit direction or on audit-related policies and communicate concerns and suggestions from external parties. They also have their Civil Petitions reception and their Citizen Auditor system.
SAI India’s social audit model
SAI Honduras model of conducting public meetings
SAI USA’s model of engaging the National Academy of Sciences and
SAI Philippines’ model of citizen participatory audit

## Slide 5: Research objectives (1)
To identify mandates/functions of SAIs and related public Audit Processes and the strategies/models they used in engaging with citizens and CSOs.
To identify the various models of Citizen Engagement/participation used by SAIs in other areas of governance.
To identify the procedures adopted by SAIs in engaging with Citizens under various models.
Notes: For this Research Project we have formulated the following objectives:
To identify mandates/functions of SAIs and related public Audit Processes and the strategies/models they used in engaging with citizens and CSOs.
To identify the various models of Citizen Engagement/participation used by SAIs in other areas of governance.
To identify the procedures adopted by SAIs in engaging with Citizens under various models.
To identify the legal bases used by SAIs in in engaging with CSOs in the performance of their mandates
To identify how CSOs are organized, how they push for advocacies, how they obtain and are provided with logistical support and how they have partnered with government entities. The challenges encountered and how they met these challenges.

## Slide 6: Research objectives
To identify the legal bases used by SAIs in in engaging with CSOs in the performance of their mandates
To identify how CSOs are organized, how they push for advocacies, how they obtain and are provided with logistical support and how they have partnered with government entities. The challenges encountered and how they met these challenges.
Notes: For this Research Project we have formulated the following objectives:
To identify mandates/functions of SAIs and related public Audit Processes and the strategies/models they used in engaging with citizens and CSOs.
To identify the various models of Citizen Engagement/participation used by SAIs in other areas of governance.
To identify the procedures adopted by SAIs in engaging with Citizens under various models.
To identify the legal bases used by SAIs in in engaging with CSOs in the performance of their mandates
To identify how CSOs are organized, how they push for advocacies, how they obtain and are provided with logistical support and how they have partnered with government entities. The challenges encountered and how they met these challenges.

## Slide 7: Research group members
Project Leader: Guatemala
Project Vice Leader: Philippines
Afghanistan
Bangladesh
Bhutan
Denmark
ECA
Iraq
India
Maldives
Myanmar
Nepal
Pakistan
Suriname
Uganda
Zambia
Notes: The following SAIs (16) have been invited to be part of this Research Initiative.
We have received the participants from:
Bangladesh, European Court of Auditors, India, Maldives, Pakistan and Uganda.

## Slide 8: Research group members
Project Leader: Guatemala
Project Vice Leader: Philippines
Afghanistan
Bangladesh
Bhutan
Denmark
ECA
Iraq
India
Maldives
Myanmar
Nepal
Pakistan
Suriname
Uganda
Zambia
Notes: The following SAIs (16) have been invited to be part of this Research Initiative.
We have received the participants from:
Bangladesh, European Court of Auditors, India, Maldives, Pakistan and Uganda.

## Slide 9: Project design
Project Scope
Various SAIs ‘ experiences on engaging with CSOs in the performance of their mandates/functions
The legal and technical bases for these engagements
Country experiences of their CSOs on engaging with Government Entities
Meeting challenges they encountered
Notes: Project Scope
The Research will cover various SAIs ‘ experiences on engaging/partnering with CSOs in the performance of their mandates/functions and the legal and technical bases for these engagements/partnerships;
Country experiences of their CSOs on organizing, pushing for their advocacies, obtaining logistical support, engaging/partnering with Government Entities and meeting challenges they encountered.
Target Groups are INTOSAI Members who have experience in working with CSOs

## Slide 10: Project design
Member SAIs of INTOSAI who have experience in engaging
with CSOs
Target Groups

## Slide 11: Project design
Planned Methodology
For Research Objectives 1,2,3 and 4:
Obtain Data from SAIs through a Country Experience Document
For Research Objective 5:
Obtain Data from citizens/CSOs who have partnered with SAIs through a Citizen Experience Document

## Slide 12: deliverables
CASE DOCUMENT
Country Experiences on Citizen Engagement in the Public Audit Process and Other Activities of SAIs
CONTENTS
SAI and Civil Society Partnerships in the Public Audit Process
SAI and Civil society Partnerships in Other Activities
Citizen/CSO Experiences

## Slide 13: Project milestones
Preparing the First draft
Review of the first Draft
Reception of suggestions to consolidate PID second draft
Review of 2nd draft and Revising PID
Reviewing of KSC
Revising PID 2nd draft
Finalizing PID and sending to KSC, Leader, Vice-Leader and Team Members
Project Initiation Documents Activities
Notes: We are currently finalizing the PID and if approved after this presentation we will be sending to the KSC, Leder, Vice-Leader and all Team Members

## Slide 14: Research work plan activities
Preparing the Research Work Plan in a meeting with the Project Team
Review of Literature
Data Gathering from SAIs and partner CSOs
Submitting Annual Progress Report to KSC
Data Processing and Writing of Research Output
Review by Leader and Vice-Leader
Project Plan Activities

## Slide 15: Research work plan activities (2)
Review by KSC
Revising the Research Output
Review by Member Sais
Revising the Research Output
Second Review by KSC and Revising the Research output
Finalizing the Research Output and Submitting to KSC
Project Plan Activities
Notes: The Research Work Plan, include activities on the design, testing and finalization of the data gathering tools (Country Experience Document for SAIs & Citizen/CSO Experience Document for citizen/CSO partners) which will be the main sources of information for writing the main Research Output which is the Case Document: Country Experiences on Citizen Engagements/ Partnerships in the Public Audit Process and Capacity/Competency Building Activities of SAIs. It will also include activities on the processing of the data gathered, writing the research output, reviewing and revision of the research output. The Project Group members and even the Project leader and vice-leader who will be responsible for specific activities in the Research Work Plan will also be identified.
The Research Work Plan will be prepared by the Research Group, following the milestones identified in the Project Work Plan.

## Slide 16: Quality assurance
This Research will adopt Level 1 of the Quality Assurance.
The QA activities have been considered in the preparation of the Project Plan Activities.
Notes: Pursuant to the 15th May 2017 document on Quality Assuring INTOSAI Public Goods that are Developed and Published Outside Due Process a Joint Paper from the INTOSAI Goal Chairs and the INTOSAI Development Initiative (IDI), this Research will adopt Level 1 of the Quality Assurance. The QA activities have been considered in the preparation of the Project Plan Activities.

## Slide 17: For your approval please
Notes: Thank you. That ends our presentation of the PID and We are now submitting the PID for the approval of the body.

## Slide 18: Thank you
Research Project
on
Citizen Participation in Public Audit