## Slide 1
PROGRESS REPORT Research Project on Auditing Emergency Preparedness of Disaster
9th KSC meeting
Bali, 23rd August 2017
Notes: Good afternoon ladies and gentlemen.
Thank you for the time given to the Audit Board of the Republic of Indonesia to present progress report of research project on Auditing Disaster Preparedness.

## Slide 2: AGENDA
1
2
3
GENERAL OVERVIEW
PROJECT DESIGN
PROPOSED DELIVERABLE
Notes: We will deliver this session into three agenda: general overview of the project, project design, and proposed deliverable.
General overview will bring us to get acknowledged with project background, project objectives, responsible SAIs, activities and coordination arrangement, and progress to date. Meanwhile, project design will look at project scope, planned methodology, and timeframe of this project. Then, we will present you with proposed outline of the research project.
We also invite you to discuss issues regarding our proposed outline of the research project.

## Slide 3: 1. GENERAL OVERVIEW

## Slide 4
2trilion $ Economic loses
4.4 billion affected And claimed 1.3 million lives
Effects will be worsen In 2030
SDGs Point 1,2,3 & 16
Project BACKGROUND
Notes: Disasters have a devastating impact on development. Families lose homes, livelihoods and loved ones; communities and nations lose businesses, jobs and services; and children miss school, impacting on the quality of a generation.
Disaster impacts are already at extremely high levels - over the past twenty years, disasters from natural hazards have affected 4.4 billion people, claimed 1.3 million lives and caused $2 trillion in economic losses – and these will worsen by 2030, according to the IPCC SREX report.
Disasters have an overwhelming human, environmental and financial toll on development. This was clearly recognised in The Future we Want document which called for the building of resilience to disasters to be addressed with a renewed sense of urgency in the context of sustainable development.
Therefore, an effective emergency preparedness should be there and able to ensure that rapid, sufficient, and accurate actions are taken in and during disaster.

## Slide 5
Project BACKGROUND Cntd..
Research Project
# Strategic Goal Intosai No 3 :
Encourage SAI cooperation, collaboration, and continuous improvement through knowledge development, knowledge sharing and knowledge services
# Strategic Objective Intosai No 3.2 :
Enable wide exchange of knowledge and experience among INTOSAI members.
# Mandate of KSC:
KSC aims to support greater professionalism and continuous improvement of SAIs by pursuing the following strategic objectives : Enable wide exchange of knowledge and experience among INTOSAI members
INCOSAI XXII Resolve
in Abudabi, 2016
Experience of SAI Indonesia in Carry out of Disaster Audit

## Slide 6: Project OBJECTIVES
01
Identifying community & system preparedness
Step 1
02
Step 2
03
Derive recommendation(s) based on identified problem(s)
Step 3
Providing audit topics & case studies

## Slide 7: RESPONSIBLE SAIs
Project leader
Indonesia
Members
Austria, Bangladesh, Bhutan, Estonia, Guatemala, Iraq, Maldives, Myanmar, Nepal, Philippines, Suriname, Trinidad and Tobago

## Slide 8: ACTIVITIES & COORDINATION ARRANGEMENT
Meetings might be arranged if a need arises and upon agreement of participating SAIs. Communication and coordination among participating SAIs will be facilitated through letter, e-mail and online discussion forum, such as KSC - IDI Portal (www.intosaicommunity.org), in person meeting or other forum agreed by the partipants of this project.
Thank you and high Apreciation for SAI Austria, Guatemala and Philipines with your Comments and input during the updated of PID as below :
Austria : The type of disaster not only natural disaster however should be included the man made of disaster.
Guatemala : has recommended to add the analysis of the international agreements on disasters that each country has accepted.
Philipines : has sent the questions if the research cover to all of the phase of disaster management, that’s are : pradisaster, emergency response, & postdisaster activities

## Slide 9: PROGRESS TO DATE
Preparation
of PID
1
Revision of
PID
3
Distributing
PID
2
Draft PID
Comments from members
Revised PID

## Slide 10: 2. PROJECT DESIGN

## Slide 11: The project will emphasize on Auditing Emergency Preparedness, particularly those deal with natural disaster (man-made disaster will be taken into account considerably)
PROJECT
SCOPE

## Slide 12
E
D
C
B
A
Literature Review
Preparing case studies
Drafting (including distributing for comments & finalization)
Study of various countries experiences
FGDs
PLANNED METHODOLOGY

## Slide 13: Project ROADMAP
01
02
03
04
2017
2018
2019
Drafting PID
Distributing PID to KSC & project members
Approval of PID
PROJECT PROPOSAL
Literature studies
FGDs
Preparing case studies
Drafting
RESEARCH & DRAFTING
Distributing draft for comments
Revising draft
Finalization
COMMENTS & FINALISATION
Research project to be approved
FINAL OUTPUT

## Slide 14
No. | Activities | Timeline
1 | First draft of Project Initiation Document (PID) | February 2017
2 | Distributing PID for comments | March 2017
3 | Receiving comments and revising draft PID | March - May 2017
4 | Final version of PID and Approval of PID from KSC | June - July 2017
5 | Meeting of research project group to discuss the Project Plan (TBD) | August 2017
6 | Research, audit, and literature studies to identify the government policies | Sept 2017 – Sept 2018
7 | Reporting of research, audit & literature studies | October 2017 –October 2018
8 | Compiling and drafting the project output (research paper) | November 2018
9 | Meeting of research project group to discuss the draft of Research report(TBD) | December 2018
10 | Distributing Draft of Research Paper for comments | January 2019
11 | Receiving comments and revising draft Research Paper | February – April 2019
12 | Final version of draft research paper | May – June 2019
13 | Report to KSC | August 2019
Detail of Time Frame

## Slide 15: 3. PROPOSED DELIVERABLE

## Slide 16: OUTLINE #1
INTRODUCTION
Common phenomenon leading to disasters and their impact
Concept and definition
HOW TO PREPARE FOR DISASTER
Government’s and agencies’ policies
International agreements
Why do prepare for disaster
Limitation on Emergency Preparedness
Mobilization and availability of funding
System readiness
Community based disaster preparedness

## Slide 17: OUTLINE #2
AUDITING EMERGENCY PREPAREDNESS
Overview of related ISSAIs
CONCLUSION
Efficiency and effectiveness of emergency preparedness
Audit topic(s) on emergency preparedness
Case studies
New issues for established ISSAIs

## Slide 18: WHAT’S NEXT
Following up received comments
Distributing up dated PID and asking approval from project members and KSC
Conducting research and drafting

## Slide 19: THANKS!
Any questions?
sumaji@bpk.go.id
niluh.dwi@bpk.o.id
international@bpk.go.id