**Reporting dashboard - <** ***Working Group on SDGs and Key Sustainable Development Indicators* >**

Key to progress indicator colours

|  |  |
| --- | --- |
|  | Initiatives / projects on schedule |
|  | Initiatives / projects behind schedule |
|  | Serious difficulties being experienced – Internal factors |
|  | Serious difficulties being experienced – External factors (beyond the control of the WG) |
|  | Not yet scheduled to start |
|  | Initiatives / projects completed |

KSC work plan 2020-22

**Strategic objectives review report (<05.06.2020>)**

|  |  |  |  |
| --- | --- | --- | --- |
| **Strategic objective**  (as per SP 2017-22) | **Strategies & initiatives**  (as per SP 2017-22) | **Performance**  **indicator[[1]](#footnote-1)** | **Action items[[2]](#footnote-2)**  **and other comment** |
|  |  |  |  |
| Develop and maintain expertise in the various fields of public-sector auditing and help to provide content to the INTOSAI Framework for Professional Pronouncements. | Preparation of new INTOSAI products and product lines: The KSC, in collaboration with other INTOSAI entities, has work plans and milestones for development of new standards and guidance for consideration by the common forum, and other INTOSAI products during 2017–2022. The KSC works closely with other stakeholders to develop products for INTOSAI’s efforts to support the implementation where appropriate and contribute to the follow-up and review of the SDGs. | 1. Endorsement of the INTOSAI GUID on the audit of the use and development of Key National Indicators. | Progress to date:  The Working Group on Key National Indicators initiated a project on developing the GUID on the audit of the use and development of key national indicators. The project was completed with the endorsement of the GUID 5290 at INCOSAI XXIII in 2019. |
| 2. Initial assessment and Project Proposal to the Guidance on the audit of reliability of macroeconomic forecasts were developed. | The Working Group on KNI initiated a project on developing the Guidance on the Audit of Reliability of Macroeconomic Forecasts (out of the IFPP). The Working group then developed the Initial Assessment and the Project Proposal to the Guidance and presented it at the 9th KSC Steering Committee Meeting.  The Working Group on SDG and Key Sustainable Development Indicators as the successor of the WG on KNI continue working on this project in 2020-2022. |
| 3. Pronouncements on the SDGs auditing | The WG SDG KSDI Action plan is under consideration at the moment. Development of the Pronouncements on the SDGs auditing is under consideration by WG members. |
| Revision of ISSAI products: Annual targets for updating and revising existing standards are established for the period 2017–2022. This work is done in close collaboration with the PSC and FIPP. | **–** | **–** |
| Enable wide exchange of knowledge and experience among INTOSAI members. | INTOSAI KSC-IDI Community Portal: In close collaboration with IDI, a knowledge sharing platform to serve as the hub for knowledge sharing has been formed. | Update of the WG SDG KSDI web page into the INTOSAI KSC-IDI Community Portal | Update of the WG on SDG and Key Sustainable Development Indicators official web page into the INTOSAI KSC-IDI Community Portal  During the WG SDG KSDI kick-off meeting on July 15th, 2020 the WG Secretariat informed the WG members about the current state of the existing web pages of the WG on KNI and plans on their update under WG SDG KSDI needs. It was decided that all relevant information on the WG will be posted on the INTOSAI Community Portal page (https://www.intosaicommunity.net/KeyNationalIndicators/). The WG page at the Accounts Chamber portal will be also kept up-to-date (<http://audit.gov.ru/en/page/the-intosai-working-group-on-sdgs-and-keysustainable-development-indicators>).  News about the WG SDG KSDI activities will be also shared at the XXIII INCOSAI twitter and web page (<https://incosai2019.ru/en>).  Information related to the WG on KNI activities will be archived under special folder on the INTOSAI Community Portal. |
| Research projects: The KSC leads the development of a scheme for encouraging internal (to INTOSAI) and external research projects in public audit. The KSC also facilitates INTOSAI’s engagement with the academic community on issues of mutual interest and concern. | Survey on SAIs’ approaches to assessing the impact of the COVID-19 crisis on the implementation of the Agenda – 2030 | The WG SDG KSDI Action plan is under consideration at the moment. The WG members discuss the feasibility of a Survey on SAIs’ approaches to assessing the impact of the COVID-19 crisis on the implementation of the Agenda – 2030. |
| Generation and dissemination knowledge and experiences. (workshops, training, benchmarking exercise, joint/ collaborative audits, outreach activities etc.)[[3]](#footnote-3) | Training | In accordance with the draft WG SDG KSDI Action Plan 2020 – 2021 the Working group consider plans to initiate a Pilot Project on training course on the SDGs auditing for the CIS member states. |
| Workshops | Working group discuss the possibility to organize:   * Videoconference with representatives of key international organizations on the SDGs issues and possible cooperation; * Videoconference with WG members, GIZ and AFROSAI-E on the PFM Reporting Framework. |
| Newsletter | At the first meeting the Working group decided to publish the WG SDG KSDI Newsletter aiming to cover the WG meetings’ results as well as SAIs’ experience in SDGs audit and reviews of relevant international projects and research concerning the SDGs. The WG Newsletter was launched in August 2020, the second issue is planned for publication in November 2020.  WG plans to issue Newsletter twice a year. |
| Working with the CBC, IDI, and other INTOSAI entities, facilitate continuous improvement of SAIs through knowledge sharing on the crosscutting lessons learned from the results of peer reviews and SAI PMF. | Stakeholder engagement: The KSC, other strategic goal committees, IDI, INTOSAI regional organizations, the Supervisory Committee on Emerging Issues and the INTOSAI General Secretariat work together to avoid duplication of work and for greater synergy. | Cooperation with the INTOSAI bodies in the development and promotion of the draft Guidance on the audit of reliability of macroeconomic forecasts and future pronouncements of the Working Group on the SDGs related topics. | While developing the Guidance and future WG pronouncements we plan to organize information exchange with the INTOSAI Working Groups (WG on Environmental Auditing, WG on IT Audit, WG on Big Data, WG on Fight Against Corruption and Money Laundering etc.) and Goal Committees, INTOSAI regional organizations, INTOSAI General Secretariat and IDI and other relevant stakeholders. |
| Facilitate continuous improvement: Working with the CBC, IDI, and other INTOSAI entities, the KSC gathers and disseminates crosscutting lessons learned from the individual results of peer reviews and of SAI PMF assessment. | Exchange of experience in the field of SDGs implementation | The Working group is ready to exchange experience in the field of SDGs implementation and promotion of Sustainable Development, and use methodological developments in this area (especially concerning the ISAM model). |
| Cooperate with and leverage the efforts of The International Journal of Government Auditing and the General Secretariat to expand the use of social media, video, and interactive tools to ensure “real-time” communication across INTOSAI, its partners, and with other interested parties. | Participation in the preparation of information on the Working Group activities | The WG Secretariat is ready to collaborate and prepare for the Journal the information about the Working Group on SDG and Key Sustainable Development Indicators, its actual goals and objectives. |

1. In the case of single large projects / initiatives, the progress indicator could also be one of the following three progress statements: (i) the project has been initiated/come into existence (has been defined, planned , and resourced), (ii) the project is being implemented (and is on track, or behind schedule, in trouble – green or amber or red/Purple), and (iii) the project has delivered the main outcome (is either completed – black – or its outcome is functioning as intended / producing the results, e.g. a technical support function; maintain, monitor and enhance). Appropriate colour may be chosen as the background of the cell. [↑](#footnote-ref-1)
2. SP 2017-22, page 36, refers to the strategic objectives review to include “determining what actions and next steps are most needed to ensure continued progress towards each objective”. The progress achieved till date and the key items/next steps needed to ensure continued progress towards each objective and to manage risks may be indicated here. [↑](#footnote-ref-2)
3. A row may be added for each activity like Workshop, trainings, benchmarking exercise, joint/ collaborative audits, outreach activities etc. [↑](#footnote-ref-3)